## Owner (hidden)
Current Status | (blank)
Row Labels | Count of Owner
Jeeva | 12
Logesh | 12
Madhav | 12
Mohan | 12
Tejeswar | 12
(blank)
Grand Total | 60

## Summary
Current Status | (blank)
Row Labels | Count of Owner
Jeeva | 12
Logesh | 12
Madhav | 12
Mohan | 12
Tejeswar | 12
(blank)
Grand Total | 60

## Custom Tasks List
S.No. | Custom Tasks Description | Delivered Custom Task Name | Priority | Current Status | Owner | Internal APIs Coverage |  | Comments | Workflow Attached | Are you Blocked | Blocked Reason | Effort Estimation Dev (Hrs) |  |  | Comments
[6 empty] | Class | Internal APIs |  |  |  |  | Conversion | UT | Code Review
1 | Getting inputs from Service Request.Fetching input values of task by passing SRID and inputFieldName(applicable for mapped input) | GetInputValueBySRID |  |  | Tejeswar |  |  | Original version of custom task code was not using the right class. Resolved that issue.
2 | CreateVMComputePolicy | CreateVMComputePolicy | P1 | Completed | Apparao | InfraPersistentUtil,VDCUtil | getPrivateCloudComputingPolicy, getVDC, persistPrivateCloudComputingPolicy |  | Yes | No
3 | CreateVMStoragePolicy | CreateVMStoragePolicy | P1 | Completed | Apparao | InfraPersistentUtil,VDCUtil | getPrivateCloudStoragePolicy, getVDC, persistPrivateCloudStoragePolicy |  | Yes | No
4 | CreateVMNetworkPolicy | CreateVMNetworkPolicy | P1 | Completed | Apparao | InfraPersistentUtil,VDCUtil | getVDC, getPrivateCloudNetworkPolicy, getPrivateCloudNetworkPolicyNICDefStr, persistPrivateCloudNetworkPolicy |  | Yes | No
5 | Ping to port task | Ping Test | NA | NA |  |  |  | Not Required. Internal APIs not used.
6 | How to insert output POWERSHELL_COMMAND_RESULT into the body of email? | Format_powershell_output | NA | NA | Logesh |  |  | Not Required. Internal APIs not used. | Yes | NA | NA
7 | UCSD Cloupia Classes : This is one of the method to get details of email setting without UI | Get Email Settings | GAP |  |  |  |  | Identified as GAP
8 | Looking for cloud in VDC | Update SysPolicyToVDC | P1 | In Progress | Logesh | VDCUtil | getVDCByName, modifyVDC |  |  | No |  | 3 | 2
9 | OVF deployment custom task - passing attributes to vCenter | Modify vDC VM Property Attribute | P1 |  | Logesh | VDCUtil,InfraPersistentUtil | getVDC, getAccount, |  |  | No |  | 3 | 4
10 | Best way to use Storage Tier option for Self Services - Need response for customer implementation | Provision Multiple VMwareVMs |  |  | Tejeswar
11 | Generate Customer Billing Report based on the Customised date | EmailChargebackReportsFromDate_ToDate |  |  | Logesh
12 | Email VM RDP (RDP) File | Send mail with attaching rdp file |  |  | Tejeswar
13 | Rollback multiple SR | Rollback_SRs | NA | NA |  |  |  | Not required. Internal APIs not used.
14 | IP Pool Custom Task | CreateStaticIPPoolPolicy | P1 | Blocked | Mohan |  |  |  | Yes | Yes | REST API not Available
15 | Netsmart is in need of a storage custom task | CreateVMwareDatastoreClusterStoragePolicy | P1 |  | Mohan
16 | Failure Email | GetWorkflowExecutionStatus |  |  | Logesh
17 | SCSI Controller type question | modifySCSIController | P1 | In Progress | Jeeva |  | ctxt.getAPI.getVMBasicInfo, |  |  |  |  | 6 | 2
18 | Create VM Disk - Thick Provision Eager Zeroed | Create vm disk with eager zero and rollback |  |  | Tejeswar
19 | Automation Backup of UCSD workflows | ExportUCSDAssets |  |  | Tejeswar
20 | [NOMURA] how to change Cluster in Computing Policy by any task/WorkFlow | ModifyComputePolicyCluster |  |  | Madhav |  |  |  | Yes | No | NA | 12 | 6
21 | Memory Reservation in UCSD 5.4 : To reserving memory of a VM | VmMemoryReservation |  |  | Madhav
22 | Schedule Workflow Programmatically : This is one of generic operation to scheduling workflow task | ScheduleWorkflowTask |  |  | Tejeswar
23 | Custom Script - Resize LUN | Get_Volume_Size |  |  | Logesh
24 | Custom Task for VM info details : To get VM details(VM IP,DNS Server IP) | VmwareVM InventoryCollector Custom Task |  |  | Logesh
25 | Assign Catalogs to group | Assign_Catalog_To_Group | P1 | In Progress | Madhav | VDCUtil | getGroup, getVDCCatalogItem, getCatalogItemName, modifyVDCCatalogItem |  | Yes | No | NA | 8 | 4
26 | Get Output Field Lists for a Custom Task | Get_OutputFieldList_Custom_Task |  |  | Jeeva
27 | Custom Task Needed | NetApp_Identity |  |  | Madhav |  |  |  | Yes | No | NA | 12 | 6
28 | AOS POC need a few custom tasks...please... | Create_Storage_Policy_Custom_Task | P1 |  | Jeeva |  | addUCSStoragePolicy |  |  |  |  | 6 | 2
29 | AOS POC need a few custom tasks...please... | Create_Network_Policy_Custom_Task | P1 |  | Madhav |  | addUCSNetworkPolicy |  | Yes | No | NA | 12 | 6
30 | AOS POC need a few custom tasks...please... | Create_ServiceProfile_Template_Custom_Task | P1 |  | Madhav |  | getUCSNetworkPolicyByAccAndName, getUCSStoragePolicyByAccAndName, performServiceProfileTemplateAction
31 | Change Initiating User for an SR | ChangeSRInitiatingUser |  |  | Madhav
32 | Resend Automated Scheduled Monthly Bill Report | Monthly_Billing |  |  | Madhav
33 | Bulk account import | BulkAccountImport |  |  | Madhav
34 | BNPP: Cloupia Script code to add a comment to requisition | SR Comments |  |  | Madhav
35 | Delete all VMs From a group | DeleteAllVMsFromGroup |  |  | Mohan
36 | workflow to delete a reserved vlan id | FreeVlanIdFromPool |  |  | Tejeswar |  |  |  |  | No |  | 8 | 8
37 | 631939549 - Production UCS Director Not processing SR | Delete All Service Request |  |  | Logesh
38 | SR 632260611 : UCSD 5.0 : unable to add VM disk larger than 2TB | diskResize_Custom_Task |  |  | Mohan
39 | VMWareVMSummary | Rename_Folder_Custom_Task | NA | NA |  |  |  | Not Required. Internal APIs not used.
40 | UCSD Custom Task | MonthlyReport CSV |  |  | Mohan
41 | Molina issue fix | RegisterTabularLOV |  |  | Logesh
42 | File Browser | FileBrowser | NA | NA | Logesh |  |  | User story in GB
43 | [Unified Computing System (UCS)] - REST API from UCSD | Execute_RestAPI | P1 |  | Mohan
44 | Custom Task to trigger re-inventory | Custom Task to Trigger inventory |  |  | Mohan
45 | Changed Subject: Rollback workflows called from Cloupia script | WFExport-143da874ac9.wfd |  |  | Mohan
46 | Are you online? | Modify VMware Deployment Policy | P1 |  | Jeeva |  |  |  |  | No |  | 6 | 2
47 | VM with physical LUN on storage mapped as RDM | Map_LUN_as_RDM |  |  | Jeeva
48 | Custom Task to trigger re-inventory(Create NetApp Account) | CreateNetAppAccount.wfdx | P1 |  | Jeeva | InfraPersistenUtil,InfrastructureDataUtil | testConnection, isValidAccountForDC, persistInfraAccount, getInfraAccountsBydcNameAndServerAddress, getAccount |  |  | No |  | 8 | 4
49 | convert policyname into as ipPoolPolicyselector | policynameToIpPoolPolicyselectorCoverter |  |  | Jeeva
50 | custom script for creating static ip pool policy | Static IP Pool Policy.wfdx | P1 |  | Mohan | InfraPersistenceUtil ,PrivateCloudStaticIPPool,VMWareUtils | PrivateCloudStaticIPPoolPolicy, PrivateCloudStaticIPPool, FormManagedList, getPrivateCloudStaticIPPoolDefStr, persistPrivateCloudStaticIPPoolPolicy, getPrivateCloudStaticIPPoolPolicy |  | Yes | Yes | REST API Not Available
51 | test all UCSM account connectivity in a given POD name | TestAccountConnection.wfdx |  |  | Jeeva | InfrastructureDataUtil | getAllInfraAccounts,getInfraAccountsByDC
52 | custom task for invoking cloudsense reports (host, VM, and cloud performance) | CloudUtilizationMonitor.wfdx |  |  | Jeeva
53 | JSON Challenged...please help...(Get VMID from SR using JSON Object) | VMIDFromSRWF.wfdx |  |  | Jeeva
54 | Create new Datastores challenge (Map LUN to Netapp Initiator Groups) | MapLUNToIGrpsWF.zip |  |  | Logesh
55 | Storage, Compute and system policies via workflow | TenantPolicy.wfdx |  |  | Logesh
56 | Delete a folder in VMWARE | FolderDelete.wfdx | NA | NA |  |  |  | Not required. Internal APIs not used.
57 | API Features | Get_VMs_By_UserID.zip |  |  | Logesh
58 | userAPIGetVMSnapshotDetails | Hyperv_Snapshots.wfdx |  |  | Tejeswar |  |  |  |  | No |  | 8 | 6
59 | Code to remove ESXi Cluster | RemoveESXiCluster.wfdx | P1 |  | Tejeswar | InfraPersistentUtil | getAccount
60 | Update on App Container VLAN Custom Task | ServiceContainerTask.wfdx |  |  | Tejeswar
61 | UCSD Orchestration workflow to pick up XML input from a file | ReadFromXML.wfdx | P1 |  | Tejeswar |  | NA
62 | Molina Issues - CSCup52117 - getAPI().userAPIGetUserLoginProfile() failing in post provisioing | Login Profile.wfdx | P1 | In Progress | Jeeva | InfraPersistenceUtil,GroupManagerImpl | getLoginUser,getGroup |  |  | No |  | 4 | 2
63 | Map shared datastores LUNs to a new host in the cluster | Map_DS_VNXLUNs_Host |  |  | Tejeswar
64 | Script for creating datacenter | Create_Datacenter.wfdx | P1 |  | Mohan | InfraPersistentUtil | getAccount, |  | Yes | No |  | 4 | 2
65 | [Cisco Developed Integrations] - How to change a VM Label in UCSD | ModifyVMLabel.wfdx | P1 | In Progress | Jeeva |  | getVMDataByVMId, getStore, VMUserData, |  |  |  |  | 4 | 2
66 | workflow to get all vm information in an array | GetAllVmDetailsInArray.wfdx | P1 |  | Mohan |  | ctxt.getAPI().userAPIGetAllVMs, APINameValueList |  | No | No |  | 4 | 2
67 | Cloupia Script to ASSIGN VMs to Groups | AddVMtoGroup.wfdx | P1 |  | Mohan |  | getGroup, getVMDataByVMId, ctxt.getAPI().getVMBasicInfo, getHyperVVMSummary, assignGroupToVM, VMUserData, assignGroupToVM |  | Yes
68 | How to get UUID | GetUUID1.wfdx |  |  | Madhav
69 | vFiler volumes | Get NetApp Volume.wfdx |  |  | Madhav |  |  |  | Yes | No | NA | 8 | 4